## Slide 1
Project Name : Completion of Jeddah-Makkah Direct Road
Contractor : Hawazen Al-Jazira Contracting Company
Consultant: Eurogroup Engineering Consulting.
Owner : Ministry Of Transport And Logistic services

## Slide 2
Award Date : | 30/05/2023
Duration of Contract: | (1080) Days
Contractual Completion Date: | 26/04/2026
Original Contract Value : | SAR 277,996,169.50
Variation in Contract Amount: | SAR 307,995,786.45
Variation in Contract Completion date: | 08/09/2027
Value of Work Completed : | SAR 177,163,457.48
% age of Work Completed : | 57.52%
General Information

## Slide 3
Construction of Road Include :
Part2 :Earthwork ( Cut – Fill – subgrade-Structural Excavations for Bridges & Culverts )
Part3 : Aggregate Base Course
Part4 : Bituminous Construction (Bituminous Primer Coat, MC-1- Bituminous Base Course Superpave PG(76-10) - Bituminous Wearing Course Superpave PG(76-10) )
Part5 : Concrete, Steel and Structure (3 Valley Bridge – 12 Box culverts)
Part6 : Incidental Construction(New Jersey Concrete Barrier, Curbstone, Catch Basin, Manholes, Inlets And Drainage Grates, Riprap And Slope Protection)
Part7 : Roadway Lighting
Part9 : Traffic Control Devices (Road Marking And Traffic Signs)
Project Description

## Slide 4
Project General Location

## Slide 5
Original Scope of Work
The Original Scope of Work includes the completion of the Jeddah-Makkah direct road from station (53+525) to station (64+500) according to Design plans, with the intersection with the Fourth Ring Road at the station (65+500).
Length = 12.00 KM.
Right of way : 100 m
dualization ( Every side 4 lane & 2 shoulders)
pavement layers:
sub grade : 30Cm
Aggregate Base course : 30 cm
Bituminous Base Course : 20 Cm
Bituminous Wearing Course : 5Cm

## Slide 6
Sub-Contracts
 | Scope of Work | Value US$ | Subcontractor Name
1 | New Jersey concrete barriers | 1,066,667 | Nahdat Al-Ejtizaz Contracting
2 | Execution of bridges and culverts | 4,000,000 | Rukn Al-Tameer Company

## Slide 7
Human Resources
 | Position | Number of Resources on the project (related to your company only)
1 | Management & Administration | 1
2 | Project Cost & Scheduling | 1
3 | Project Managers | 1
4 | Senior Design Engineers | 2
5 | Design Engineers | 1
6 | Project Engineers | 2
7 | HSE Manager/Officer | 2
8 | Procurement Personnel | 1
9 | Quality Department Personnel | 3
10 | Construction Supervisors | 4
11 | Construction Skilled Labor | 145
12 | Construction Unskilled Labor | 10
Total |  | 173

## Slide 8
List Of Equipment
 | Description | Number
1 | Bulldozer | 8
2 | Grader | 6
3 | Excavator | 12
4 | Roller Compactor | 11
5 | Water Tanker | 8
6 | Loader | 6
7 | Truck | 48
8 | Crane | 7
9 | Concrete Pump | 3
10 | Concrete Mixer | 10
11 | Asphalt Paver | 2
12 | Crusher | 2
13 | Concrete patch Plant | 1
14 | Asphalt Patch Plant | 2
15 | MC-1 Tanker | 1
16 | Steel Roller Compactor | 2
17 | Wheels Roller | 4
18 | Small Loader | 2
19 | Fuel Tank | 2
20 | Car Maintenance | 3
Total |  | 140

## Slide 9
Typical Cross section

## Slide 10
Completion Rate of the Project to Date

## Slide 11
Excavation
Use of Explosives

## Slide 12
Rock Excavation

## Slide 13
Earthwork (Fill)

## Slide 14
Earthwork (Fill)

## Slide 15
Earthwork (Fill)

## Slide 16
Earthwork (Subgrade)

## Slide 17
Aggregate Base Course

## Slide 18
Aggregate Base Course

## Slide 19
Aggregate Base Course

## Slide 20
Aggregate Base Course

## Slide 21
Bridges

## Slide 22
Bridges

## Slide 23
Bridges

## Slide 24
Box Culvert

## Slide 25
Box Culvert

## Slide 26
Bridges

## Slide 27
Bridges

## Slide 28
Bridges

## Slide 29
Bridges

## Slide 30
Bridges

## Slide 31
Crushers

## Slide 32
Asphalt Plant

## Slide 33
End of presentation